## Scorecard Production View
|  | Friday after Corrections File load | Production M-W | Delivery on Friday | 1 week to meet w/ Plans | Via Initial File | Via Corrections File
Scorecard Query Month | Months of Service Contained | DW Run Query | DGRS Report Production | Scorecard Delivery | Meet with Plans | Corrections Round 1 Due | Corrections Round 2 Due
2018-08-01 | 3/18 | 2018-08-10 | 2018-08-15 | 2018-08-17 | 8/20/18 - 8/24/18 | 2018-08-31 | 2018-09-12
2018-09-01 | 3/18, 4/18 | 2018-09-14 | 2018-09-19 | 2018-09-21 | 9/24/18 - 9/28/18 | 2018-09-30 | 2018-10-10
2018-10-01 | 3/18, 4/18, 5/18 | 2018-10-12 | 2018-10-17 | 2018-10-19 | 10/22/18 - 10/26/18 | 2018-10-31 | 2018-11-14
2018-11-01 | 3/18, 4/18, 5/18, 6/18 | 2018-11-16 | 2018-11-21 | 2018-11-23 | 11/26/18 - 11/30/18 | 2018-11-30 | 2018-12-12
2018-12-01 | 4/18, 5/18, 6/18, 7/18 | 2018-12-14 | 2018-12-19 | 2018-12-21 | 12/24/18 - 12/28/18 | 2018-12-31 | 2019-01-09
2019-01-01 | 5/18, 6/18, 7/18, 8/18 | 2019-01-11 | 2019-01-16 | 2019-01-18 | 1/21/19 - 1/25/19 | 2019-01-31 | 2019-02-13
2019-02-01 | 6/18, 7/18, 8/18, 9/18 | 2019-02-15 | 2019-02-20 | 2019-02-22 | 2/25/19 - 3/1/19 | 2019-02-28 | 2019-03-13
2019-03-01 | 7/18, 8/18, 9/18, 10/18 | 2019-03-15 | 2019-03-20 | 2019-03-22 | 3/25/19 - 3/29/19 | 2019-03-31 | 2019-04-10
2019-04-01 | 8/18, 9/18, 10/18, 11/18 | 2019-04-12 | 2019-04-17 | 2019-04-19 | 4/22/19 - 4/26/19 | - | -
2019-05-01 | 9/18, 10/18, 11/18, 12/18 | - | - | - | - | - | -
2019-06-01 | 10/18, 11/18, 12/18, 1/19 | - | - | - | - | - | -
2019-07-01 | 11/18, 12/18, 1/19, 2/19 | - | - | - | - | - | -

## Encounter Data Submission View
|  |  | EOM | Subsequent Wed. | Subsequent Wed. |  | EOW | M-W Production | EOW |  |  |  | Subsequent Wed.
| Encounter Data Dates of Service | Month of Service | Initial File Submission | Initial File Load | Corrections File Submission | Corrections File Load | DW Run Query | DGRS Report Production | Scorecard Delivery | Meet with Plans | Corrections Round 1 Due | Corrections Round 2 Due | Manual Override Submission | Manual Override Load
2018-03-01 | 3/1/18 - 3/31/18 | 2018-03-01 | 2018-04-30 | 2018-05-02 | 2018-05-09 | 2018-05-09 | 2018-08-10 | 2018-08-15 | 2018-08-17 | 8/20/18 - 8/24/18 | 2018-08-31 | 2018-09-12 | 2018-05-16 | 2018-05-16
2018-04-01 | 4/1/18 - 4/30/18 | 2018-04-01 | 2018-05-31 | 2018-06-06 | 2018-06-13 | 2018-06-13 | 2018-09-14 | 2018-09-19 | 2018-09-21 | 9/24/18 - 9/28/18 | 2018-09-30 | 2018-10-10 | 2018-06-20 | 2018-06-20
2018-05-01 | 5/1/18 - 5/31/18 | 2018-05-01 | 2018-06-30 | 2018-07-04 | 2018-07-11 | 2018-07-11 | 2018-10-12 | 2018-10-17 | 2018-10-19 | 10/22/18 - 10/26/18 | 2018-10-31 | 2018-11-14 | 2018-07-18 | 2018-07-18
2018-06-01 | 6/1/18 - 6/30/18 | 2018-06-01 | 2018-07-31 | 2018-08-01 | 2018-08-08 | 2018-08-08 | 2018-11-16 | 2018-11-21 | 2018-11-23 | 11/26/18 - 11/30/18 | 2018-11-30 | 2018-12-12 | 2018-08-15 | 2018-08-15
2018-07-01 | 7/1/18 - 7/31/18 | 2018-07-01 | 2018-08-31 | 2018-09-05 | 2018-09-12 | 2018-09-12 | 2018-12-14 | 2018-12-19 | 2018-12-21 | 12/24/18 - 12/28/18 | 2018-12-31 | 2019-01-09 | 2018-09-19 | 2018-09-19
2018-08-01 | 8/1/18 - 8/31/18 | 2018-08-01 | 2018-09-30 | 2018-10-03 | 2018-10-10 | 2018-10-10 | 2019-01-11 | 2019-01-16 | 2019-01-18 | 1/21/19 - 1/25/19 | 2019-01-31 | 2019-02-13 | 2018-10-17 | 2018-10-17
2018-09-01 | 9/1/18 - 9/30/18 | 2018-09-01 | 2018-10-31 | 2018-11-07 | 2018-11-14 | 2018-11-14 | 2019-02-15 | 2019-02-20 | 2019-02-22 | 2/25/19 - 3/1/19 | 2019-02-28 | 2019-03-13 | 2018-11-21 | 2018-11-21
2018-10-01 | 10/1/18 - 10/31/18 | 2018-10-01 | 2018-11-30 | 2018-12-05 | 2018-12-12 | 2018-12-12 | 2019-03-15 | 2019-03-20 | 2019-03-22 | 3/25/19 - 3/29/19 | 2019-03-31 | 2019-04-10 | 2018-12-19 | 2018-12-19
2018-11-01 | 11/1/18 - 11/30/18 | 2018-11-01 | 2018-12-31 | 2019-01-02 | 2019-01-09 | 2019-01-09 | 2019-04-12 | 2019-04-17 | 2019-04-19 | 4/22/19 - 4/26/19 | - | - | 2019-01-16 | 2019-01-16
2018-12-01 | 12/1/18 - 12/31/18 | 2018-12-01 | 2019-01-31 | 2019-02-06 | 2019-02-13 | 2019-02-13 | - | - | - | - | - | - | 2019-02-20 | 2019-02-20
2019-01-01 | 1/1/19-1/31/19 | 2019-01-01 | 2019-02-28 | 2019-03-06 | 2019-03-13 | 2019-03-13 | - | - | - | - | - | - | 2019-03-20 | 2019-03-20
2019-02-01 | 2/1/19-2/28/19 | 2019-02-01 | 2019-03-31 | 2019-04-03 | 2019-04-10 | 2019-04-10 | - | - | - | - | - | - | 2019-04-17 | 2019-04-17
Formulas:
Subsequent Wed. = DATE(YEAR([EOM]+1),MONTH([EOM]+1),1)+MOD(11-WEEKDAY(DATE(YEAR([EOM]+1),MONTH([EOM]+1),1)),7)
Subsequent Wed. = [Subsequent Wed.]+7
Corrections File Load = [Subsequent Wed.]
EOW = [M-W Production]+2
M-W Production = [EOW]+5
Manual Override Load = [Subsequent Wed.]